ClientEnforce

Master Operating Guide

What happens when. Who owns it. How we know it worked.

Document 5 of 6 — read after Docs 01-04.

Owner: Thomas — info@clientenforce.com

Last updated: 10 May 2026

# 1. How to use this guide

This guide turns the 4 strategy docs into a calendar. If you're staring at your screen on a Tuesday morning wondering what to do, this is the document you open. Daily rituals (Section 2), weekly rituals (Section 3), the 90-day calendar (Section 5), and decision rules (Section 7).

Three habits to internalise:

- Time-block, don't task-list. Marketing happens in the blocks below or it doesn't happen at all.

- Process before output. The point of the rituals is consistency. Skipping one ritual creates two days of catch-up.

- Friday-review religiously. Weekly review is where the system improves. Skip it and the system drifts.

# 2. Daily operating rhythm — the time blocks

Marketing time = 27 hours/week (~5.5 hrs/day Mon-Fri). Realistic for a founder splitting time with product/sales. Block these times in your calendar; treat them as customer meetings.

## 2.1 The Mon-Fri daily template

| Time block | Activity | Detail |
| --- | --- | --- |
| 08:00 - 08:15 | Morning open | Open KPI Dashboard (Trackers Sheet 02). Note any red. Triage urgent. |
| 08:15 - 08:45 | Cold email triage | Check all 4 Instantly inboxes. Reply within 1 hour to anything positive. Mark negatives. |
| 08:45 - 09:30 | LinkedIn engagement | 10 thoughtful comments on ICP posts. 10 connection requests sent. Reply to all DMs. |
| 09:30 - 10:00 | Founder post + replies | Publish today's post. Reply to all comments on yesterday's post. |
| 10:00 - 12:30 | Deep work block | Highest-leverage thing of the day. Mon: list-build. Tue: SEO/content. Wed: demos. Thu: customer work. Fri: review. |
| 12:30 - 13:30 | Lunch (no screen) | Don't break this. Cognitive recovery is the multiplier. |
| 13:30 - 15:00 | Demos / sales calls / customer conversations | Calendar block — held vs available depending on bookings. |
| 15:00 - 16:30 | Product / customer support / inbox | The non-marketing 1.5 hrs. |
| 16:30 - 17:00 | Outbound finish + plan tomorrow | Last reply check. Update Trackers. Write tomorrow's top-3 priorities. |
| 17:00 | Hard stop on marketing | No LinkedIn posts after 5pm. No cold email after 5pm. Boundary. |

## 2.2 Why these blocks specifically

- Mornings = highest cognition. Cold email replies + LinkedIn comments need precision and tone.

- 10am-12:30 deep work block. The single most leveraged 2.5 hrs. Don't allow meetings in here unless they directly drive revenue.

- Demos in the afternoon. Buyer attention is fine. Founder energy is what matters.

- Hard 5pm stop on marketing. Founders burn out fast without this.

# 3. Weekly rituals

## 3.1 Monday — Plan + List Build (90 min)

| Time | What |
| --- | --- |
| 09:30 | Re-run all 5 saved Sales Nav searches. Add 50 new leads to LinkedIn outbound list. |
| 10:00 | Build cold email lists for Sequences A and B (UK + US accountants). 30 prospects per inbox = 60 prospects total. Verify in Million Verifier. |
| 10:45 | Add prospects to Instantly with personalisation tokens filled (first name, firm name, trigger event reference). |
| 11:15 | Plan the week's 5 founder posts. Write hooks for all 5. Draft Mon's post in full. |

## 3.2 Tuesday — List Build (60 min)

| Time | What |
| --- | --- |
| 09:30 | Build cold email lists for Sequences C and D (law firms + agencies). 30 each = 60 prospects. |
| 10:00 | Verify and add to Instantly with personalisation. |
| 10:30 | Tuesday SEO block (45 min): one of {cannibalisation fix / new comparison page / FAQ schema add}. |

## 3.3 Wednesday — Mid-week Health Check (30 min)

| Time | What |
| --- | --- |
| 09:30 | Deliverability check — mxtoolbox on both domains. Check spam folder on test addresses (set up a Gmail you control to receive test sends). |
| 10:00 | Wednesday DM follow-up sweep — anyone who accepted a connection 2-3 days ago and hasn't been DM'd. 30 min. |
| 10:30 | Mid-week deep work block (case study writing, comparison page draft, podcast outreach). |

## 3.4 Thursday — Content + Outbound Push (45 min)

| Time | What |
| --- | --- |
| 09:30 | Publish Thursday's post (carousel/document — these get 6.6% engagement vs 5.2% text). Pre-built last week. |
| 10:15 | Send 2 podcast pitches via email. Use a template (in 4.3 below). |

## 3.5 Friday — Review + Reset (90 min)

| Time | What |
| --- | --- |
| 15:30 | Update KPI Dashboard 'This Week' column with all numbers (cold sends, replies, LI metrics, signups). |
| 16:00 | Update Path to £10k MRR sheet with this week's net new paying customers + MRR. |
| 16:15 | Re-pull SEMrush position tracker. Update SEO Cannibalisation tracker status. |
| 16:30 | Open Weekly Review template. Fill in: 3 wins, 3 losses, 1 experiment for next week. |
| 17:00 | Confirm warmup-to-cold ratios on all 4 inboxes (Inbox Warmup sheet — match it). |

# 4. Monthly rituals

## 4.1 First Monday of the month — Strategy review (90 min)

- Review Path to £10k MRR vs. actual. Variance > 25%? Identify which channel under-delivered.

- Review the 7 Revenue Levers (Doc 01 § 6). Which one needs the most attention this month?

- Re-read the 3 Big Bet Campaigns (Doc 01 § 7). One of them tracking to KPO? Two of them? All three? Decide kill / extend / graduate.

- Update headlines and lead-magnets if any have stagnated for 30+ days.

## 4.2 Mid-month checkpoint (15 min)

First Wednesday after the 15th. Quick gut-check: are we on pace for monthly KPO? If MRR is < 50% of monthly target by mid-month, escalate to a 2hr emergency strategy block by EOW.

## 4.3 First Thursday — Podcast pitch batch (60 min)

Send 4 podcast pitches in one sitting. Template:

Subject: ClientEnforce founder for {{Podcast name}}? Hey {{first_name}} — Listened to your episode with {{recent_guest}} — the bit about {{specific topic}} matched what I'm seeing in the field with {{ICP}}. Quick context: I'm Thomas, founder of ClientEnforce — we work with regulated professional services firms (accountants, lawyers, agencies) on enforced client onboarding. Specific things I could talk about that your audience would care about: 1. Why client onboarding software built for photographers fails accountants (specific contrast) 2. The data on what % of intake delays are caused by the firm vs. the client (it's not what you'd guess) 3. The "no-client-login" decision: why we shipped it and the conversion lift it produced Would any of those line up for an upcoming episode? Either way, thanks for the show — keeps me thinking. — Thomas Founder, ClientEnforce clientenforce.com

# 5. The 90-day execution calendar (May - July 2026)

Week-by-week list of MUST-HAPPEN actions. Aspirations and wishlist items don't appear here.

## 5.1 Weeks 1-4 (May 11 - Jun 7) — Foundation

| Week | Action |
| --- | --- |
| Wk 1 (May 11) | URGENT: ship 8 SEO 301 redirects (Doc 04 § 5). Fix /fleet-account-onboarding canonical. Fix homepage broken link. Set up self-reported source field on /signup. |
| Wk 1 (May 11) | Start cold sending on thomas@clientenforce.com (10/day cold + 15/day warmup). Sequence A live. |
| Wk 1 (May 11) | 5 founder posts published. 50 LinkedIn connection requests sent. 50 ICP comments left. |
| Wk 2 (May 18) | Cold sends on thomas@cf rise to 15/day. First positive replies expected — reply within 1 hour. |
| Wk 2 (May 18) | Refresh /multi-location-client-onboarding (currently #1 — protect). |
| Wk 2 (May 18) | Tim @ Telletire case study interview booked (Big Bet 2 kickoff). |
| Wk 3 (May 25) | info@cf, thomas@trycf, tom@trycf go LIVE. All 4 inboxes now sending cold. Total: ~70 cold/day across 4 inboxes (thomas@cf at 20, others at 10). |
| Wk 3 (May 25) | Sequences B, C, D go live. 4 sequences across 4 inboxes. |
| Wk 3 (May 25) | Refresh /blog/best-client-onboarding-software-2026 (currently #1 — protect, prep H2 2026 ToC update). |
| Wk 4 (Jun 1) | Build /honeybook-vs-clientenforce (new comparison page). |
| Wk 4 (Jun 1) | First customer interview clip published as video post + 3 quote graphics from Tim. |
| Wk 4 (Jun 1) | M1 review: vs target 2 paid + £200 MRR. |

## 5.2 Weeks 5-8 (Jun 8 - Jul 5) — Scale

| Week | Action |
| --- | --- |
| Wk 5 (Jun 8) | thomas@cf at steady state (30/day cold). All 4 inboxes ramping. |
| Wk 5 (Jun 8) | Build /dubsado-vs-clientenforce. |
| Wk 5 (Jun 8) | Tim case study published as 2,000-word page. Promote across 5 LinkedIn posts that week. |
| Wk 6 (Jun 15) | Build /client-intake-software-for-accountants (vertical split-out). |
| Wk 6 (Jun 15) | Apply for G2, Capterra, GetApp listings. |
| Wk 6 (Jun 15) | First webinar — 'How to cut client intake from 14 days to 2'. 30-min live with Q&A. |
| Wk 7 (Jun 22) | ALL 4 INBOXES at steady state (30/day cold each = 120/day total = 600/wk). |
| Wk 7 (Jun 22) | Refresh /blog/client-onboarding-process into 3,000-word pillar. |
| Wk 7 (Jun 22) | First partnership conversation — outreach to TaxDome OR Karbon OR Practice Ignition. |
| Wk 8 (Jun 29) | Build /law-firm-client-intake. |
| Wk 8 (Jun 29) | M2 review: vs target 6 paid + £500 MRR. |

## 5.3 Weeks 9-12 (Jul 6 - Aug 2) — Compound

| Week | Action |
| --- | --- |
| Wk 9 (Jul 6) | Build /accounting-firm-onboarding-checklist (lead magnet). |
| Wk 9 (Jul 6) | Pitch + record 1st podcast appearance. Distribute clips. |
| Wk 10 (Jul 13) | Long-form: /tim-telletire-case-study published. Big Bet 2 anchor. |
| Wk 10 (Jul 13) | Re-engagement email to all trial signups from M1-M2 who didn't convert. |
| Wk 11 (Jul 20) | Build /comparison/clientenforce-vs-rocketlane. |
| Wk 11 (Jul 20) | Launch referral program (1 month free for each paying customer who refers a paying customer). |
| Wk 12 (Jul 27) | Re-run cannibalisation audit. Re-pull SEMrush. Score progress vs baseline. |
| Wk 12 (Jul 27) | M3 review: vs target 14 paid + £1,200 MRR. Quarterly strategy review. |

# 6. The trial onboarding lifecycle engine

Trial signup is the moment of highest intent. The lifecycle email sequence converts ~20% of trials to paid. Without it: ~5%. This sequence runs automatically once built. Build week 1, set and forget.

## 6.1 The 8-email lifecycle sequence

| When | Type | Subject / theme | Action we want |
| --- | --- | --- | --- |
| Day 0 | Email | Welcome — set the expectation, link to first action | Build first onboarding template |
| Day 0 + 1hr | Email (auto) | Confirm + 1-click 'send a test portal link to yourself' | Self-test the portal |
| Day 1 | Email | How {{peer_firm}} got their first portal live (case study) | Apply to your own intake |
| Day 3 | Email | Are you stuck on something? Reply for help. Founder-signed. | Reply if blocked |
| Day 5 | Email | Activation check — have you sent a portal link to a real client yet? | Send a real portal link |
| Day 7 | Email | Soft conversion — '7 days in. What does pricing look like for you?' | Upgrade to Team / Scale |
| Day 10 | Email | Tactical guide — 'The 5-step intake template that converts' | Build a 2nd template |
| Day 13 | Email | Pre-end nudge — 'Your trial ends in 24 hrs. Lock in monthly or annual?' | Pick a plan |

## 6.2 Trigger-based emails (not in main sequence)

- If user invites a 2nd team member: 'Looks like you're rolling this out across the team. Here's how the £29 Team plan saves you 4 hrs/week.' (Day-of-invite)

- If user creates 3+ templates: 'You're getting structural use out of the product. Here's what Scale unlocks.'

- If user sends 5+ portal links: 'Quick check-in from Thomas — anything I can do?'

- If user is inactive 3+ days: 'Stuck on something? Hit reply, I'll help.'

## 6.3 Lifecycle benchmarks (target rates)

| Metric | Target |
| --- | --- |
| Day 0 welcome open rate | 55%+ |
| Day 0 'send a test portal' click rate | 40%+ |
| Day 5 activation rate (sent a real portal link) | 35%+ |
| Day 13 trial → paid conversion | 20%+ |

# 7. Decision rules — when to kill / extend / escalate

Decision rules let you make calls without a 2-hour debate. Set the rule once. Apply it weekly. The discipline is in following the rule even when you don't want to.

## 7.1 Kill rules

| Channel / asset | Kill condition | Action |
| --- | --- | --- |
| Cold email sequence | Reply rate < 2% over 4 weeks | Pause sequence. Tighten ICP. Rewrite first line. Restart with 25 prospects. |
| Founder post topic | < 200 impressions on 3 consecutive posts of same type | Drop that topic for 30 days. Try different angle. |
| LinkedIn DM template | DM reply rate < 5% over 50 sends | Rewrite. A/B test 2 variants on next 50. |
| Big Bet campaign | 0% of KPO hit by month 2 | Kill at end of month 2. Replace with new big bet. |
| Comparison page | 0 organic visits in 60 days | Rewrite hook + add 5 FAQs. Re-submit to GSC. |
| Inbox | Bounce rate > 5% OR spam rate > 0.3% | Pause inbox. Quarantine list. Restart at 5/day. |

## 7.2 Escalate rules (stop everything else and address)

- MRR drops MoM. Stop everything for 1 day, run churn analysis.

- Inbox suspended by Google. Stop all 4 inboxes for 2 days. Audit everything.

- Top-3 SEO position lost. Same-day investigation. Cannibalisation, indexing, or quality issue.

- A customer requests cancellation. Personal call from Thomas within 24 hrs.

- A customer hits Scale or Agency Pro feature limits. Same-week reach-out about upgrade.

## 7.3 Graduate rules (keep doing what's working)

- Cold email reply rate > 12% on a sequence: lock the copy. Don't change.

- LinkedIn post type > 5k impressions consistently: produce 1 of that type per week minimum.

- SEO page in top 3 for high-volume keyword: refresh quarterly to defend.

- Channel delivers > 25% of new paid customers in a month: double the time/resource on it for next month.

# 8. The 6 engines (visual map)

Marketing isn't tasks — it's engines. Each engine takes inputs and produces outputs continuously. Once built, it runs without daily founder thought.

| Engine | Inputs | Outputs | Detail in |
| --- | --- | --- | --- |
| 1. Cold Outbound Engine | Apollo + Sales Nav lists, Instantly sequences, 4 inboxes | Replies → meetings → demos → trials → paid | Doc 02 |
| 2. LinkedIn Engagement Engine | Sales Nav saved searches, founder posts, 10 daily comments | Inbound DMs → demos → trials → paid | Doc 03 |
| 3. SEO + Content Engine | Cannibalisation map, content calendar, FAQ schema | Organic visits → trial signups → paid | Doc 04 |
| 4. Trial Onboarding Engine | 8-email lifecycle sequence + trigger-based emails | Trial signups → paid customers | Doc 05 § 6 |
| 5. Customer Success / Expansion Engine | Monthly check-in for Scale+, weekly product use alerts | Churn down + Team→Scale→Agency Pro upgrades | Doc 05 § 9 |
| 6. Referral / Partnership Engine | Referral program, integration partner outreach | Referrals + co-marketing leads → paid | Doc 01 § 10 |

## 8.1 Engine maturity levels

Each engine moves through three states: Building → Running → Optimising.

| State | What it looks like |
| --- | --- |
| Building (M1) | Set up infrastructure. Write first sequences. Configure tools. |
| Running (M2-M3) | Engine produces output without daily intervention. Founder monitors weekly. |
| Optimising (M4+) | A/B test variants. Compound the engine. Hire to scale it. |

# 9. Customer success / expansion ritual

Net revenue retention > 100% is what makes B2B SaaS a great business. Most early-stage founders ignore CS. We don't. With ~3 customers in M1 and ~115 in M7, the founder can do CS personally. By M9 we hire.

## 9.1 Per-customer cadence by tier

| Plan | Touch cadence |
| --- | --- |
| Solo (free) | Monthly automated email check-in. No founder time. |
| Team (£29) | Day-7 founder welcome video. Day-30 check-in email. Day-60 upgrade prompt to Scale. |
| Scale (£89) | Day-1 founder welcome call (15 min). Monthly 15-min health check. Quarterly NPS ask. |
| Agency Pro (£149) | Day-1 white-glove onboarding call (30 min). Bi-weekly check-in for first 60 days. Monthly thereafter. Dedicated Slack channel. |

## 9.2 Churn-risk signals

- Login activity drops to zero for 7+ days → automated re-engagement email + founder DM.

- Active onboardings drops vs. previous month → founder check-in within 7 days.

- Support ticket about cancellation or 'how do I export my data' → personal call from Thomas same day.

- Failed payment → 3 retries over 7 days, then personal email from Thomas.

# 10. Things to build/fix this week (the gap list)

Items that BLOCK execution. Each must have a date next to it. If a gap stays open longer than 14 days it gets escalated to 'pause everything else and fix this'.

| Gap | Why it matters | Owner / Date | Status |
| --- | --- | --- | --- |
| Self-reported source field on /signup | Without it, channel attribution is guesswork. | Mon 11 May | Open |
| UTM tagging on every external link | Required for source attribution. | Wed 13 May | Open |
| 8 SEO 301 redirects (Doc 04 § 5) | Cannibalisation = capped SEO results. | Fri 16 May | Open |
| Fix homepage broken link to /onboarding-for-agencies | Homepage card links to non-existent page. | Mon 11 May | Open |
| Calendar booking link in email signature + footer | Direct path from cold reply to demo booked. | Tue 12 May | Open |
| Lifecycle email sequence (Loops or similar) | 20%+ of conversion depends on it. | Fri 23 May | Open |
| HubSpot Free OR Notion CRM | Single pipeline view = no deals lost to follow-up gaps. | Wed 14 May | Open |
| Tim @ Telletire interview | Big Bet 2 anchor. Single most important content asset of the quarter. | By 22 May | Open |

# 11. Escalation triggers (the alarms)

| Trigger | Response |
| --- | --- |
| MRR misses month target by > 25% | Same week strategy block. Re-evaluate channel mix. |
| Cold email reply rate < 2% across all 4 inboxes for 2 weeks | Pause all sends. Ground-up ICP review. |
| Inbox flagged or restricted by ESP | Pause domain. Audit DNS. Investigate complaints. |
| A #1 ranking lost | Same-day cannibalisation check + recovery action. |
| A paying customer cancels | Personal call from Thomas within 24 hrs. Document the cancellation reason. |
| A demo no-show > 30% | Reschedule cadence broken. Add 1-hr-before reminder + same-day reschedule link. |
| Founder bandwidth overflow (> 35 hrs/wk on marketing) | Re-evaluate priorities. Drop the lowest-leverage engine for 1 week. |

# 12. Compliance + governance baseline

## 12.1 GDPR / UK GDPR

- Maintain LIA (Legitimate Interest Assessment) document in Notion for cold email.

- Process opt-outs within 24-48 hours into Suppression List (Trackers Sheet 11).

- Never email a suppressed contact from any of the 4 inboxes.

- Honour data subject access requests within 30 days.

## 12.2 CAN-SPAM (US)

- Real physical postal address in every email footer.

- Honest subject lines (no clickbait, no false 'Re:' prefixes).

- Functional unsubscribe link in every email.

## 12.3 Customer data (Stripe + Supabase)

- Customer payment data lives in Stripe. We never store card numbers.

- Audit trail / customer documents lives in Supabase + S3-compatible storage. Encrypted at rest.

- DPA available on request for any customer that asks.

# 13. Monthly report-out template

First Friday of every month. Take this template, fill it in, share with self (or Slack to a channel of one). Builds discipline.

# {{Month}} {{Year}} — Marketing Report-Out ## The numbers - Net new paying customers: ___ (target: ___) - MRR end of month: £___ (target: £___) - Trial signups: ___ - Cold email replies: ___ - LinkedIn DM conversations: ___ - Organic visits: ___ ## Path to £10k MRR — where we are - Cumulative paying customers: ___ / 115 needed - Months remaining: ___ - Required net new per month from here: ___ - On track / behind / ahead: ___ ## What worked 1. ___ 2. ___ 3. ___ ## What didn't work 1. ___ 2. ___ 3. ___ ## What we're changing for next month 1. ___ (because: ___) 2. ___ (because: ___) 3. ___ (because: ___) ## Big Bet status - Stop Chasing: ___ - Tim @ Telletire case study: ___ - Apples to Apples: ___ ## Customer notes - New customers (named): ___ - Churn (named, with reason): ___ - Upgrades (named): ___ ## Asks / unblocks - ___ - ___

# 14. The one-paragraph operator summary

Marketing is a calendar, not a task list. 27 hrs/week split across 6 engines (cold outbound, LinkedIn, SEO + content, trial onboarding, CS/expansion, referrals/partnerships). Daily template: 30 min cold-email triage, 45 min LinkedIn engagement, 30 min founder post + replies, 2.5 hr deep work block, demos in afternoon. Weekly: Mon list-build + plan, Tue list-build + SEO block, Wed mid-week health check, Thu carousel post + podcast pitches, Fri review and reset (90 min — non-negotiable). Monthly: first-Monday strategy review, mid-month gut-check, big-bet kill/extend/graduate decisions. The 90-day calendar in Section 5 says exactly what ships in which week. Decision rules in Section 7 govern when to kill, extend or escalate without debate. The lifecycle email engine in Section 6 converts trial → paid at 20%+. The customer success cadence in Section 9 protects MRR. Owner of every engine: Thomas, until M9 hire.